## スケジュール
工程管理・スケジュール表
※発表は含んでいません |  | 9/19 | 9/20 | 9/21 | 9/22 | 9/23 | 9/24 | 9/25 | 9/26 | 9/27 | 9/28 | 9/29 | 9/30 | 10/1 | 10/2 | 10/3 | 10/4 | 10/5 | 10/6
全体進捗率 |  | 資料 | 資料 | 休み | 休み | 休み | 休み | 資料 | 資料 | 資料 | ソース | 資料 | 休み | 休み | 資料 | ソース | 資料 | ソース | ソース
%
書類 | 担当 | 進捗 | 9/19 |  |  | 9/20 |  |  | 9/25 |  |  | 9/26 |  |  | 9/27 |  |  | 9/28 |  | 9/29 | 10/2 | 10/3 | 10/4 | 10/5 | 10/6
要件定義書 | 黒田・森岡 永井 | 50% | 要件定義書作成 |  |  | 永井：全体的に確認・修正 |  |  | 森岡：画面遷移図修正 |  |  | 森岡：画面遷移図大幅に修正
基本設計書 | 黒田 | 70%
アーキテクチャー図 | 黒田・森岡 | 80% | 黒田,森岡：作成 | [8 empty] | 森岡、黒田：アーキテクチャ図作成
クラス定義書 | 永井 | 80% | 永井：DAO,DTOクラス定義書
データーベース設計書(SQL) | 永井 | 0%
操作説明書（アプリ操作説明） | 田中 | 50% |  |  |  | 田中：操作説明書作成 | [5 empty] | 田中：操作説明書作成
テスト仕様書(動作確認事項表作成) |  | 20% |  |  |  | 永井：動作確認、修正
テスト(テスト仕様書＞実際の動作確認)
デバック(動作確認＞修正作業)
レビュー（先生の評価） |  | 0%
レビュー（先生の評価）＞修正作業
発表準備（パワーポイント）実習向け
発表
デザイン | [8 empty] | 永井：css修正 |  |  | 永井：css
ソース | 担当 | 進捗 | 9/19 |  |  | 9/20 |  |  | 9/25 |  |  | 9/26 |  |  | 9/27 |  |  | 9/28 |  | 9/29 | 10/2 | 10/3 | 10/4 | 10/5 | 10/6
Detail.java |  | 100%
ExecuteDeleteMeibo.java |  | 100%
ExecuteDeleteShinamono.java |  | 100%
ExecuteEditShinamono.java |  | 100%
ExecuteSignup.java |  | 100%
Logininfo.java |  | 100%
Logoutinfo.java |  | 100%
MainPage.java |  | 100%
MeiboEntry.java |  | 100%
ShinamonoEntry.java |  | 100%
ShowAllMeibo.java |  | 100%
ShowAllShinamono.java |  | 100%
DetailBL.java |  | 100%
ExecuteSelectMeiboBL.java |  | 100%
ExecuteSelectShinamonoBL.java |  | 100%
InsertMeiboBL.java |  | 100%
InsertShinamonoBL.java |  | 100%
MeiboDAO.java |  | 100%
MeiboDTO.java |  | 100%
ShinamonoDAO.java |  | 100%
ShinamonoDTO.java |  | 100%
ShowAllMeiboBL.java |  | 100%
ShowAllShinamonoBL.java |  | 100%
SignupBL.java |  | 100%
UpdateMeiboBL.java |  | 100%
UpdateShinamonoBL.java |  | 100%
UserInfoDao.java |  | 100%
UserInfoDto.java |  | 100%
error.html |  | 100%
finish.html |  | 100%
detail.jsp |  | 100%
editmeibo.jsp |  | 100%
editshinamono.jsp |  | 100%
login.jsp |  | 100%
logout.jsp |  | 100%
mainpage.jsp |  | 100%
meiboentry.jsp |  | 100%
shinamono_entry.jsp |  | 100%
showallmeibo.jsp |  | 100%
showallshinamono.jsp |  | 100%
signup.jsp |  | 100%
DeleteCheck.java | 黒田 | [7 empty] | 黒田：webapp連結 |  |  | 黒田：カレンダー機能の強化、誕生日が出るように
EditSchdule.java | 黒田
MonthView.java | 黒田
NewSchedule.java | 黒田
ScheduleInsert.java | 黒田
ScheduleView.java | 黒田